Project Charter

UBC IT Intranet Project

Deirdre Rogers January 10, 2011

Document Revision History

| Version | Date | Author(s) | Description of Change |
| --- | --- | --- | --- |
| 1.0 | Jan. 10, 2011 | Deirdre Rogers | Created |
| 1.2 | Jan. 17, 2011 | Deirdre Rogers | Revisions based on meetings with technical team |
| 1.3 | Jan, 31,2011 | Deirdre Rogers | Revisions based on input from Claudio Pini and Julie Kothlow, Liza Jose, and vendor |

Table of Contents

I.	Project Background	4

II.	Project Purpose and Objectives	4

III.	Project Benefits	5

IV.	Project Scope	5

1.	Deliverables	7

2.	Assumptions	7

3.	Dependencies	7

V.	Project Approach	8

VI.	Critical Success Factors	10

VII.	Project Risks	10

VIII.	Project Organization	11

Project Authorization	13

Appendices	14

Appendix A:  Project Schedule	14

Appendix B:  Project Budget	14

# Project Background

The UBC IT Intranet project is an outcome of the CCIS (Communication, Collaboration and Information Sharing) project that took place in the fall on 2010.   As a function of the CCIS initiative, the team achieved the following:

- Conducted an audit of current tools used for communication and collaboration

- Conducted surveys and focus groups to determine UBC IT staff and stakeholder group communication requirements

- Developed business and functional requirements for a corporate intranet

- Designed and tested an information architecture based on the requirements

- Recommended that Microsoft SharePoint 2010 be the technology platform

- Recommended that a communications framework, with clear communication channels and ownership be defined and established as part of the Communications strategy.

- Recommended that an appropriate governance plan and related policies be developed and implemented with active participation of a governance committee.

# Project Purpose and Objectives

The purpose of this project is to improve productivity, and effectiveness of communication and collaboration within the UBC IT department.   This will consist of:

- Designing the SharePoint architecture and infrastructure that will support not only this deployment but any future deployments by other departments;

- Building a new corporate intranet, based on Microsoft SharePoint 2010, by April 30, from the wireframes and information architecture developed in the CCIS project;

- Designing a more engaging and interactive site through the use of effective graphic design and branding;

- Designing a communications framework that overhauls existing communications and channels, and support distributed authoring;

- Creating a governance committee;

- Developing and implementing an effective governance structure that supports a distributed content model and establishes clear ownership and policies;

- Implementing a more effective search engine, with appropriate taxonomy;

- Identifying key content to be available at launch and for other content develop a content migration plan approved by the Governance committee.

# Project Benefits

The project will deliver the following benefits:

- Increased productivity through better organization and search tools enabling staff to locate information quickly and easily;

- Reducing information redundancy by creating a central content repository;

- Providing targeted and more effective communication through an overhaul of existing communication pieces and channels;

- Increased collaboration through the use of current tools such as blogs and wiki;

- Increased employee engagement through the use of leading edge social media tools, new branding and identity of the intranet.

Finally, planning for and providing an architecture that enables easy deployment of future SharePoint sites university-wide creates a value-added service which the department can then offer within the University.

# Project Scope

| This Project Includes: | This Project Does Not Include: |
| --- | --- |
| - The building and launch of a corporate intranet: - Develop project charter and plan - Develop a communications and change management plan - Develop a new graphic branding and identity - Develop an architecture that supports the new site as well as lays the foundation for future sites deployed as part of a UBC IT service. - Build and test the site - Develop content migration plan (with key content identified as part of the initial launch, other content migrated at a later date as per a detailed migration plan) - Develop launch plan - Execute all comm., change, and launch plans - Develop Communications Framework: - Determine existing communication needs and delivery mechanisms - Match messaging with new channels - Establish clear guidelines, standards, and ownership for both communication pieces and communication mediums - Governance Policy & Plan - Convene interim governance committee - Develop governance policy - Approval by SMT - Hand-off to final governance committee - Support & Sustainment - Roles and responsibilities clearly defined - Production Turn-over document - All technical documentation developed - Accepted by Help Desk | - Content migration (including Confluence content.) Key content will be identified and made available at launch. A detailed content migration plan will be developed and filed with the governance committee to manage post-launch. - Developing customized training materials (insufficient budget). |

## Deliverables

Project Charter & Plan

Architecture diagrams (UBC IT site and roadmap for foundation)

Technical documentation

Fully functioning and tested intranet site

Communications Framework

Governance Policy and Plan

Production Turn-Over document

## Assumptions

- SharePoint architecture developed by outside vendor;

- Senior technical support outsourced to assist internal technical resources;

- Selection of EAD for authentication;

- Software licensing finalized (campus-wide agreement) within the Microsoft 90 day window;

- Availability of content owners to migrate/redevelop content (for initial launch);

- Availability of internal graphic designer to complete the graphic design and branding of the site;

- Availability of sustainment resources (specifically SQL).

## Dependencies

- EAD project needs to be complete within UBC IT department .

# Project Approach

The project team will build the new intranet site based on the requirements and the information architecture wireframes developed as part of first phase of the project.  As per the recommendations, a communications framework will be developed aligning communications with the new intranet channels.  Finally, a governance policy and plan will be developed and put into effect prior to launching the site.

To support this site and any future requests for SharePoint sites, the architecture will be designed and implemented to align with the existing UBC IT infrastructure.  This will be done utilizing an external vendor working with internal infrastructure resources.

As requested by the SMT, the site will be developed and populated with initial key content.  A content migration plan will be developed with the expectation that groups will be migrating content for several months post -launch according to an agreed upon plan.

The project will be divided into three streams that will run concurrently:

- Technical – focused on the foundation architecture and building out the site as per the wireframes;

- Content – finalizing content, content ownership and channels, and preparing the content inventory and migration plan;

- Governance – developing and implementing the appropriate governance policy and plan.

Finally, the project will look to leverage team resources within the Med IT project that will be underway at the same time (kick-off is mid-February and launch is planned for October, 2011).

| UBC IT Intranet Site Build | Jan | Feb 1 -4 | Feb 7-11 | Feb 14-18 | Feb 21-28 | Mar 1-4 | Mar 7-11 | Mar 14-18 | Mar 21-25 | Mar 28-31 | Apr 1-8 | Apr 11-15 | Apr 18-22 | Apr 25-29 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project planning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Initial Change Management, Communication, Training and Launch Planning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Branding, identity & graphic design |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Architecture planning and roadmap |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Site build out |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Testing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Content Migration Planning (audit, inventory, classification, mapping) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Develop Communications Framework |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Support & Sustainment Planning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Develop Governance Policy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| New Content Creation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| *Initial Content Migration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Change Management Execution |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Communications Execution |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Training Delivery |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Go-Live |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Support & Sustainment Implementation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Production Turn-Over |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

*Key content will be identified and migrated to site upon launch, other content migrated by users at a later date (according to plan filed with governance committee

# Critical Success Factors

- Resources – the appropriate resources need to be available for each ‘stream’ of the project– technical, content, and governance;

- Authentication – for the project to be a success, all authentication issues need to be resolved to ensure proper access for all;

- Senior Management Support – this will ensure full participation leading up to launch and especially afterwards;

- Communications and change management plan – developed and executed throughout the project and after launch until all content is migrated.

# Project Risks

| Risk | Probability | Consequence | Mitigation |
| --- | --- | --- | --- |
| Resource Risk – Availability of Project Team | High – Team members could be pulled onto other higher priority tasks or projects | schedule impact | Escalate to Steering Committee to ask for prioritization direction and/or to communicate to staff. |
| Authentication | High – EAD migration not be finalized in time OR if Shibboleth then project delay | Schedule impact, quality impact | Authentication decision made quickly and work on other non-dependant areas so that all is ready when auth finalized. |
| Content Migration | High – all content will not be migrated upon launch | User adoption could be effected. | Identify critical content for homepage and file plan for balance of migration – find creative ways to involve/entice users to migrate their content. |
| Budget Constraints | Medium – Budget is small with no room for contingency | May impact scope and timeline | Look for ways to leverage by partnering with Med IT |

# Project Organization

The following table identifies the roles and responsibilities of the project team members:

| Role | Responsibilities |
| --- | --- |
| Executive Sponsor | - Acts as the project champion and communicates project mandate to the organization - Authorizes resources for the project - Ultimate decision-maker for the project - Measures and evaluates success of the project; accountable for the project benefits |
| Steering Committee | - Provides oversight for the project - Monitors progress and results - Resolves conflicts and removes barriers for project progress - Authorizes changes to scope, schedule, budget |
| Project Manager | - Accountable for the completion of the project deliverables - Manages the project budget and team resources - Manages issues and risks - Manages changes through CAB process - Escalates issues to the Steering Committee when required |
| SharePoint Architect Senior Technical Resource VENDOR | - Designs the foundational architecture - Designs the SharePoint h/w, s/w architecture for IT site - Determines how best to integrate with infrastructure - Planning for site features, customizations, site and list relationships - Liaises with infrastructure group during initial software installation, troubleshooting - Details disaster recovery specs - Details capacity plans - Details network security - Defines and configures search - Implements branding strategy |
| Technical Advisor | - Input and approval of all technical documents - Mentors/supports technical lead - Coordinates with infrastructure group re authentication |
| Technical Lead SP Developer | - Manages the technical components of the project plan - Builds out the site according to wireframes and specifications - Develops necessary templates, web parts - Skins new site with graphic design by applying CSS files - Delivers a fully functional, tested and de-bugged SharePoint 2010 as per specs and wireframes |
| Business Analyst | - Build-out the lower level wireframes - Assists with any content migration prior to launch - Acts as information architect |
| Communications & Change Management Lead | - Prepares and manages communications and change management plan - Acts as lead on communication framework |
| Content Lead | - Supports the content category owners and ensures content ready for launch |
| Content Category Owners | - Participates in content planning meetings - Contributes to content migration plan by identifying content critical for launch and/or later migration - Develops/assigns content to be developed for launch |
| Content owners | - May need to develop some content for launch. |
| Interim Governance Committee | - Develops governance policies and plan by participating in facilitated workshops |
| Governance Committee | - As part of the final plan, communicates ownership to respective team members. - Enforces policy |
| SharePoint administrator | - Assists in build as part of knowledge transfer - Takes appropriate training to be able to support the site after launch |

# Project Authorization

The signatures below represent an authorization to proceed with the project as defined in this Charter document including Appendices.

| Role | Name & Title | Date |
| --- | --- | --- |
| Executive Sponsor |  |  |
| Steering Committee Member |  |  |
| Project Manager |  |  |

# Appendices

## Appendix A:  Project Schedule

Attach Project Schedule as an Appendix to the Project Charter.

## Appendix B:  Project Budget

Attach Project Budget as an Appendix to the Project Charter.  Template is available on the PMO site.

NOTE: BEING FINALIZED BASED ON SCOPE DECISIONS BY STEERING COMMITTEE

Additional Appendices may be added as required, e.g. Communications Plan, Impact Assessment, Change Management Strategy.  See the PMO site for any available templates.